## Sheet1
Count of ID | Column Labels
Row Labels | High | Low | Medium | Urgent | Very High | (blank) | Grand Total
Closed | 18 | 17 | 6 | 9 | 14 |  | 64
Deferred | 2 | 3 | 1 |  |  |  | 6
Fixed | 9 |  |  | 2 | 3 |  | 14
In Progress |  | 1 | 1 |  |  |  | 2
New |  | 1 | 5 |  |  |  | 6
Review |  | 6 | 6 |  |  |  | 12
(blank)
Grand Total | 29 | 28 | 19 | 11 | 17 |  | 104

## Sheet2
Row Labels | High | Low | Medium | Urgent | Very High | (blank) | Grand Total
Closed | 18 | 17 | 6 | 9 | 14 |  | 64
Deferred | 2 | 3 | 1 |  |  |  | 6
Fixed | 9 |  |  | 2 | 3 |  | 14
In Progress |  | 1 | 1 |  |  |  | 2
New |  | 1 | 5 |  |  |  | 6
Review |  | 6 | 6 |  |  |  | 12
Grand Total | 29 | 28 | 19 | 11 | 17 |  | 104

## Data
Name | ID | Creation time | Has attachments | Priority | Severity | Phase | Detected by | Detected in release | Release | Owner | Last modified | Milestone | Environment | Current Date | Date Difference
"Terms of Use" page is not displaying | 999760 | 2023-05-05 18:01 | Yes | Medium | High | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 53
View Invoice' link on Account Balance should display only open invoices | 988167 | 2023-04-13 19:10 | Yes | High | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-28 23:49 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 75
About myCoke page Layout - Page Body Text is hidden behind image | 1012101 | 2023-05-29 15:32 | Yes | High | Low | Fixed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-02 22:47 | MyCoke360 UAT |  | 2023-06-27 19:37 | 29
Account Balance & Recently Paid content running out of the sections | 988172 | 2023-04-13 19:14 | Yes | Very High | Very High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Gourav Kumar | 2023-04-21 23:04 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 75
Account balance and Recently paid sections are of different height | 988166 | 2023-04-13 19:04 | Yes | Low | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-28 23:53 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 75
Account Balance content - Not aligning as per Figma for both bottlers storefronts | 990345 | 2023-04-17 16:03 | Yes | Medium | Medium | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-15 17:24 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 71
Account Blocked message retained when switched to unblocked account | 1004317 | 2023-05-13 01:18 | Yes | High | High | Fixed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-30 17:59 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 45
Account list section disappear when we click on the header of list section | 999603 | 2023-05-05 13:30 | Yes | High | Medium | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 02:11 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 53
Account Switcher collapses - intermittent | 1004367 | 2023-05-13 01:58 | Yes | Medium | Low | Review | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-06-01 03:56 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 45
After Refresh, Paid invoices are also displaying under Open invoices Tab. | 995050 | 2023-04-26 17:30 | Yes | Very High | Medium | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 02:27 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 62
After User is disabled from storefront user is not grayed out until page is refreshed manually by user | 1002440 | 2023-05-10 17:53 | Yes | Low | Medium | Review | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-05-11 17:42 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 48
Asterisk mark is coming before last name field in my profile page . | 1005035 | 2023-05-15 15:40 | Yes | Low | Low | Review | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-24 04:51 | Digital Strategy Phase 1 - MyCoke360 | QA, Safari | 2023-06-27 19:37 | 43
Authenticated /Guest User HomePage - Footer Design - Horizontal Bar is not displaying | 989156 | 2023-04-14 18:59 | Yes | Low | Low | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-29 00:17 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 74
Authenticated Dashboard - Pay Now | 988193 | 2023-04-13 19:18 | Yes | Urgent | Very High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Vibhu Tyagi | 2023-05-03 14:31 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 75
Authenticated Header - 'Invoices' link & layout not matching Figma | 989470 | 2023-04-15 | Yes | High | Medium | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 02:25 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 73
Authenticated Header - On Hover, Color is NOT Changing to RED | 989127 | 2023-04-14 18:46 | Yes | Low | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-29 00:13 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 74
Blocker- New user onboarding flow | 1006927 | 2023-05-18 18:13 | Yes | Urgent | Critical | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 40
Bottler Admin is not able to view Builder and workspace option in experience builder | 1001737 | 2023-05-09 16:04 | Yes | Very High | High | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Vishal Tiwari | 2023-05-26 17:56 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 49
Bottler Employee registering new Users has no access to Externally managed account & Sharing setting | 1008738 | 2023-05-23 01:16 | Yes | Urgent | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-02 22:49 | MyCoke360 UAT | Chrome | 2023-06-27 19:37 | 35
Bottler's Storefronts - Invoice detail page - Not Consistent | 992712 | 2023-04-21 16:04 | Yes | High | Medium | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-05-16 02:27 | Digital Strategy Phase 1 - MyCoke360 | IE | 2023-06-27 19:37 | 67
Bulk Edit Menu Display NOT as per Figma | 990217 | 2023-04-17 14:55 | Yes | Medium | Medium | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-28 23:54 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 71
Contact Us - for 'become a customer' some fields are missing | 991316 | 2023-04-18 18:00 | Yes | High | High | Deferred | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Vishal Tiwari | 2023-04-27 07:33 | Digital Strategy Phase 1 - MyCoke360 | Staging | 2023-06-27 19:37 | 70
Count of Open/Closed Invoice not matching from Snowflake | 1002369 | 2023-05-10 07:50 | Yes | High | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-05-10 22:50 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 48
Edit user page layout is not as per figma | 1001078 | 2023-05-08 17:10 | Yes | Low | Medium | Review | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-05-12 20:15 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 50
Error message is displaying at Welcome Email | 1006932 | 2023-05-18 18:33 | Yes | High | High | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 40
Error Message is displaying_On My Profile_Update Button Click | 999841 | 2023-05-05 19:30 | Yes | High | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 00:22 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 53
Error message is showing when we submit Dispute form for both Consolidated and SWIRE | 995010 | 2023-04-26 15:54 | Yes | High | High | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-04-28 20:48 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 62
Experience Builder_ All Site_ Error Message Pop up is displaying on Page change | 1011619 | 2023-05-26 18:34 | Yes | High | Medium | Fixed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-07 19:25 | MyCoke360 UAT |  | 2023-06-27 19:37 | 32
FAQ Page in Swire is Displaying Content from both SWIRE & Consolidated | 1025434 | 2023-06-26 22:42 | Yes | Medium | Medium | New | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Vibhu Tyagi | 2023-06-27 09:20 | MyCoke360 UAT |  | 2023-06-27 19:37 | 1
FAQ page layout not consistent across Storefronts and Unauthenticated Page | 995433 | 2023-04-27 13:12 | Yes | Very High | Low | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Gourav Kumar | 2023-05-16 02:27 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 61
Footer - 'term of use' is not in single line | 991260 | 2023-04-18 15:39 | Yes | Low | Medium | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Gourav Kumar | 2023-04-28 22:55 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 70
Footer - background not white and terms , privacy disclaimers with padding below | 996019 | 2023-04-28 20:01 | Yes | Medium | Low | Review | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-04-29 01:17 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 60
Header - Username is displaying inside user profile Logo | 989136 | 2023-04-14 18:49 | Yes | Low | Medium | In Progress | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Aneesh Singh | 2023-05-18 17:57 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 74
Homepage Footer - Copyright Year Is missing | 989106 | 2023-04-14 18:33 | Yes | Low | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-02 23:45 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 74
Homepage Header - Help dropdown - 'Contact us' need to be in one line | 991140 | 2023-04-18 03:44 | Yes | Low | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-28 23:02 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 70
Homepage Header - User Profile DropDown - 'My Profile' display NOT in one line | 989148 | 2023-04-14 18:52 | Yes | Low | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-28 23:35 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 74
ICEP_ SNAPPAY, Login to Snap pay button is not displaying from ICEP Home page and Account Page. | 1006930 | 2023-05-18 18:23 | Yes | High | High | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 40
In Contact Us Page, State field is not showing options according to country selected | 991343 | 2023-04-18 19:24 | Yes | Low | Medium | Deferred | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Yashodarshan Kalmanoor | 2023-04-27 07:11 | Digital Strategy Phase 1 - MyCoke360 | Staging | 2023-06-27 19:37 | 70
In ICEP, Related Manage Account list, the nomenclature of the relation updated from Storefront is not displaying as expected. | 1020011 | 2023-06-12 14:50 | No | Medium | Medium | New | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Vibhu Tyagi | 2023-06-13 02:53 | MyCoke360 UAT |  | 2023-06-27 19:37 | 15
In ICEP_ Experience Builder & Digital Experience App, CMS is not display for Bottler Admin | 1010638 | 2023-05-25 09:06 | Yes | Urgent | Very High | Fixed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-02 03:43 | MyCoke360 UAT |  | 2023-06-27 19:37 | 33
In Storefront, Myprofile section, All User First Names are followed by Additional ! Sign | 1012708 | 2023-05-30 19:57 | Yes | Medium | Medium | New | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-09 18:29 | MyCoke360 UAT |  | 2023-06-27 19:37 | 28
In User List Page, Account Popup list is NOT aligned, when user scrolls down with multiple linked account. | 1013117 | 2023-05-31 16:43 | Yes | Medium | Medium | New | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-09 18:25 | MyCoke360 UAT | Safari | 2023-06-27 19:37 | 27
Invoice _BULK Download – Only 2 pdf downloads when more then 2 invoices selected | 990460 | 2023-04-17 16:58 | Yes | Very High | High | Fixed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-02 22:26 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 71
Invoice Detail Page - Back Button | 993107 | 2023-04-22 02:22 | Yes | Low | Medium | Review | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-05-10 20:09 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 66
Invoice Detail Page does not have data in fields | 1001600 | 2023-05-09 04:56 | Yes | Very High | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 49
Invoice Details Page - Email function not as expected | 990524 | 2023-04-17 17:28 | Yes | Medium | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Jyotika Pandey | 2023-05-02 23:47 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 71
Invoice list - Font size is not as per Figma | 991219 | 2023-04-18 13:32 | Yes | Low | Medium | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Srikanth N | 2023-05-16 02:27 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 70
Invoice list _" From and To " Date field are mandatory field in Custom date range without select any date "done " button is clickable and not showing any error message. | 1012237 | 2023-05-29 16:55 | Yes | Medium | Low | Deferred | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-01 00:52 | MyCoke360 UAT |  | 2023-06-27 19:37 | 29
Invoice page - Invoice Account Balance section NOT aligned (For Swire) | 991193 | 2023-04-18 13:06 | Yes | Low | Medium | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 02:27 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 70
Invoice Page Detail - Invoice Number not displayed | 988195 | 2023-04-13 19:24 | Yes | Low | Low | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 75
Invoice selected on first page retains same selection across pages | 1002193 | 2023-05-09 23:12 | Yes | High | Medium | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 49
Invoices - Bulk email NOT working instead it is downloading PDF | 990346 | 2023-04-17 16:06 | Yes | High | Very High | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 02:27 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 71
Invoices List - 'Action' column name NOT in Bold | 989359 | 2023-04-14 20:56 | Yes | Low | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-29 00:22 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 74
Invoices List - No Column sorting available | 991125 | 2023-04-18 03:27 | Yes | High | High | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-29 00:28 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 70
Invoices List - Open Tab displaying Disputed invoices | 991087 | 2023-04-18 03:06 | Yes | Low | Medium | Deferred | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Jyotika Pandey | 2023-04-24 15:40 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 70
Invoices Page Filter - Operands are not relevant to every field (User Experience) | 991099 | 2023-04-18 03:16 | Yes | High | High | Deferred | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 |  | 2023-04-25 02:23 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 70
L org- Invoice Page-In Storefront Consolidated Bottler : Date range is not displayed correctly (overlapping) at 100%. | 1009961 | 2023-05-24 15:25 | Yes | High | Medium | Fixed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Gourav Kumar | 2023-06-02 17:08 | MyCoke360 UAT | Chrome | 2023-06-27 19:37 | 34
L org-double line on expanding and blue line is displayed on FAQ page. | 1009060 | 2023-05-23 15:48 | Yes | High | Medium | Fixed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-29 17:56 | MyCoke360 UAT | Chrome | 2023-06-27 19:37 | 35
L Org-G3 Bottler sites: After logging in to the G3 bottlers getting error with blank page. | 1024351 | 2023-06-23 11:41 | Yes | Very High | Critical | Fixed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Neha Basutkar | 2023-06-23 15:55 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 4
Login to Snappay button(Home page) is not navigating to SnapPay page. | 1001631 | 2023-05-09 13:18 | Yes | Urgent | Medium | Fixed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-02 22:38 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 49
Mobile Header - Profile dropdown | 996017 | 2023-04-28 19:52 | Yes | Low | Medium | Review | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-04-29 01:16 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 60
My Profile Page_ Phone & Email_Label Name NOT Matching with Figma | 999758 | 2023-05-05 17:50 | Yes | Medium | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 53
My Profile_ Contact Number field is Not Editable | 999825 | 2023-05-05 19:15 | Yes | Low | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 53
My Profile_Change Password field is also displaying in "Profile Edit" Page. | 1001883 | 2023-05-09 18:53 | Yes | Medium | Medium | Review | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-05-10 19:10 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 49
Next page is still enabled and Invoice data is displaying again in the Next Page - When Page Row Count is MORE THAN Invoice Count | 990582 | 2023-04-17 17:58 | Yes | High | Very High | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 71
Not able to add valid storefront user to External contact | 995211 | 2023-04-26 20:49 | Yes | High | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-04-28 22:55 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 62
Object level Permissions for B2B Standard Profile are not correct | 995473 | 2023-04-27 13:43 | Yes | Very High | Medium | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 61
On Navigating to secondary account error is encountered | 1001602 | 2023-05-09 05:07 | Yes | Urgent | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 02:25 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 49
Order Block Notification - Bell Icon NOT as per Figma | 990768 | 2023-04-17 23:09 | Yes | Low | Low | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 02:27 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 71
Permission are not given at object level to the B2B super user. | 1001005 | 2023-05-08 14:26 | Yes | High | Medium | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 00:21 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 50
Permissions not assigned to B2B Bottler Admin Permission Set | 1001066 | 2023-05-08 16:57 | Yes | Very High | Medium | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Ashley Jiang | 2023-05-26 04:56 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 50
Phone number column is not visible in User page | 1001192 | 2023-05-08 20:10 | Yes | Low | Medium | Closed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-06-13 23:43 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 50
Recently Paid - View All – 'Invoice list' NOT in descending order | 990143 | 2023-04-17 14:21 | Yes | Low | Medium | Deferred | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Yashodarshan Kalmanoor | 2023-04-25 02:18 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 71
Safari - After Clicking on "Pay Now button" still remains | 992765 | 2023-04-21 18:07 | Yes | High | Medium | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-15 17:28 | Digital Strategy Phase 1 - MyCoke360 | Safari | 2023-06-27 19:37 | 67
Search Tab on Closed Invoices Hangs on Query & Label Change | 1017567 | 2023-06-08 19:43 | Yes | High | Medium | Fixed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-12 17:53 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 19
Select multiple invoice but in email we are receiving only one invoice. | 995656 | 2023-04-27 16:32 | Yes | High | Medium | Fixed | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-02 22:24 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 61
Snowflake Due Date Incorrect | 1001577 | 2023-05-09 04:26 | Yes | Very High | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Yashodarshan Kalmanoor | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 49
Snowflake error when not available | 1023626 | 2023-06-21 03:15 | Yes | Urgent | Critical | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-27 02:16 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 6
Snowflake Invoice count not matching condition | 1000220 | 2023-05-06 02:36 | Yes | Urgent | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Vibhu Tyagi | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 52
Snowflake rendering 150K Open invoices | 1007138 | 2023-05-19 19:22 | Yes | Very High | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Yashodarshan Kalmanoor | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 39
Snowflakes integration, In Invoice list Page - Alignment issue on Amount due field | 1015940 | 2023-06-06 02:19 | Yes | Low | Low | New | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-09 12:42 | MyCoke360 UAT |  | 2023-06-27 19:37 | 21
Super user_New user creation issue | 1001483 | 2023-05-09 01:48 | Yes | Very High | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 49
Superuser - Pay Now button is getting displayed in Invoice summary page | 1015414 | 2023-06-05 18:49 | Yes | Medium | Medium | New | Vyjayanthi P | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-09 19:44 | MyCoke360 UAT |  | 2023-06-27 19:37 | 22
SWIRE_ADD USER form is not displaying | 1005094 | 2023-05-15 16:52 | Yes | Very High | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | MyCoke360 UAT |  | 2023-06-27 19:37 | 43
The Application hangs when the Account is switched | 1011537 | 2023-05-26 17:49 | Yes | High | High | Fixed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-01 01:00 | MyCoke360 UAT |  | 2023-06-27 19:37 | 32
The Dispute form - Reasons to follow a common format i.e. Pascal case for every word | 995119 | 2023-04-26 19:24 | Yes | Low | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-04-28 09:22 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 62
UI / UX Cleanup :Current Year is display twice | 1001018 | 2023-05-08 14:58 | Yes | Medium | Low | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 50
UI/ UX_Order number is not display for both bottler. | 999761 | 2023-05-05 18:03 | Yes | High | Medium | Closed | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 53
UI/UX : Typeface - Font family is not displaying as inter. | 995430 | 2023-04-27 13:04 | Yes | Medium | Medium | Review | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-04-28 15:59 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 61
UI/UX _Safari _On click on Search tab, outline is populated with blue colour box. | 995958 | 2023-04-28 15:39 | Yes | Low | Low | Review | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-04-29 01:20 | Digital Strategy Phase 1 - MyCoke360 | QA, Safari | 2023-06-27 19:37 | 60
UI/UX: Pay now button UI Remain Same for all Button Actions types Unlike as per FIGMA Style Guide | 995442 | 2023-04-27 13:28 | Yes | Medium | Medium | Review | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-04-28 22:08 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 61
Unable to create New User for L Org StoreFront - Welcome Email_ Activate Now_ link is Navigation to M Org Link instead of L Org Link | 1010784 | 2023-05-25 15:37 | Yes | Very High | Very High | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | MyCoke360 UAT |  | 2023-06-27 19:37 | 33
Unable to find the IDP Indicator filed on Contact | 1001629 | 2023-05-09 13:16 | Yes | Medium | Medium | In Progress | Neha Basutkar | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-05-12 15:36 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 49
Unable to Login into Swire Bottler | 1001135 | 2023-05-08 18:14 | Yes | Urgent | Very High | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-13 03:40 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 50
Unable to Navigate to Snappay- Due to Address details of Shipping Address Street is NULL | 1011635 | 2023-05-26 19:16 | Yes | Very High | Medium | Fixed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-07 15:30 | MyCoke360 UAT |  | 2023-06-27 19:37 | 32
UnAuthenticated Header - On hover, Color is NOT Changing to RED | 989286 | 2023-04-14 20:27 | Yes | Low | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Gourav Kumar | 2023-04-28 20:20 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 74
Unauthenticated - Hero Banner - Video is stretched | 988161 | 2023-04-13 18:56 | No | Very High | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Gourav Kumar | 2023-05-17 01:49 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 75
UnAuthenticated HomePage - Customer Stories Header - More Margin is required on Top | 989422 | 2023-04-14 22:57 | Yes | Low | Low | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 02:27 | Digital Strategy Phase 1 - MyCoke360 | Chrome | 2023-06-27 19:37 | 74
Unauthenticated- Contact Us- Contact Us (Header & Footer) link doesn't navigate to Contact Us page | 988164 | 2023-04-13 18:59 | No | Urgent | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-04-14 20:29 | Digital Strategy Phase 1 - MyCoke360 |  | 2023-06-27 19:37 | 75
Users : Account, Permissions and Last Accessed column are not aligned as per figma | 1001076 | 2023-05-08 17:02 | Yes | Medium | Medium | Review | Srikanth N | MyCoke360 R1 | MyCoke360 R1 | Manivannan Sugumar | 2023-05-12 20:14 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 50
Users that are created by Super user is not visible when we switch to Secondary Account from Storefront | 1013867 | 2023-06-01 18:54 | Yes | High | High | Fixed | Vyjayanthi P | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-07 17:38 | MyCoke360 UAT |  | 2023-06-27 19:37 | 26
Welcome Email not sent when a bottler Employee enables a customer user | 1008739 | 2023-05-23 01:22 | Yes | Urgent | High | Closed | Vibhu Tyagi | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-06-13 02:49 | MyCoke360 UAT | Chrome | 2023-06-27 19:37 | 35
Welcome Email _ SWIRE_ Email Body is populating Consolidated Template in Mail Body | 995672 | 2023-04-27 16:49 | Yes | High | High | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Sanju Yadav | 2023-05-16 00:23 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 19:37 | 61
Welcome Email_ Email Source (From email) is not as expected. | 995574 | 2023-04-27 15:12 | Yes | Very High | Medium | Closed | Jyotika Pandey | MyCoke360 R1 | MyCoke360 R1 | Vibhu Tyagi | 2023-06-13 02:49 | Digital Strategy Phase 1 - MyCoke360 | Chrome, QA | 2023-06-27 18:53 | 61

## Summary Report
Aging | Urgent | High | Low | Medium | Very High | Grand Total
< 7 |  |  |  | 1 | 1 | 2
8 - 15 |  |  |  | 1 |  | 1
16 - 30 |  | 3 | 1 | 4 |  | 8
> 30 | 2 | 8 | 10 | 7 | 2 | 29
Grand Total | 2 | 11 | 11 | 13 | 3 | 40